## sprint chart & burndown
PRODUCT BACKLOG & BURNDOWN CHART
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | END DATE | DURATION | PCT OF TIME TAKEN | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
0 | Design and Setup (early March) |  | 157 | 215 | -58 |  |  |  | 102 | 136.9%
0.1 | User stories | Entire team | 5 | 6 | -1 | 1 | 2024-03-02 | 2024-03-04 | 3 | 120%
0.2 | Function points | Entire team | 5 | 8 | -3 | 1 | 2024-03-03 | 2024-03-06 | 3 | 120%
0.3 | Container design | Entire team | 5 | 6 | -1 | 1 | 2024-03-02 | 2024-03-03 | 2 | 120%
1 | Sprint 1 (March to mid april) |  | 76 | 107 | -31 |  |  |  | 48 | 140.8%
1.1 | Container composition setup | Emanuele | 5 | 8 | 3 | 1 | 2024-03-03 | 2024-03-08 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | User model creation | Eric, Giuseppe, Alessio | 3 | 3 | 0 | 1 | 2024-03-12 | 2024-03-19 | 2 | 100% | bar: WEEK 1 W to WEEK 1 T
1.3 | User creation route (first draft) | Alessio, Giuseppe, Eric | 5 | 3 | 2 | 1 | 2024-03-29 | 2024-03-30 | 2 | 60% | bar: WEEK 1 F to WEEK 2 F
1.4 | DBMS setup and SQL interaction | Entire team | 5 | 11 | -6 | 1 | 2024-03-18 | 2024-03-30 | 13 | 220% | bar: WEEK 1 F to WEEK 2 F
1.5 | User past recommendations route, rec model | Emanuele, Emilio, Alessio | 3 | 2 | 1 | 1 | 2024-03-23 | 2024-03-23 | 2 | 66.67% | bar: WEEK 1 F to WEEK 2 F
1.6 | First CSS draft | Emilio, Eric, Giuseppe | 5 | 5 | 0 | 1 | 2024-03-23 | 2024-03-23 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
1.7 | User token route | Eric | 2 | 1 | 1 | 1 | 2024-03-23 | 2024-03-23 | 1 | 50% | bar: WEEK 1 F to WEEK 2 F
1.8 | DBMS fix | Entire team | 3 | 10 | -7 | 2 | 2024-04-08 | 2024-04-14 | 7 | 333.3%
1.9 | Switch to SQLAlchemy for DBMS | Entire team | 10 | 13 | -3 | 2 | 2024-04-16 | 2024-04-20 | 5 | 130% | bar: WEEK 2 M to WEEK 3 M
2 | Sprint 2 (Mid to late April) |  | 25 | 32 | -7 |  |  |  | 11 | 128%
2.1 | Authentication and session system | Entire team | 10 | 19 | -9 | 2 | 2024-04-08 | 2024-04-20 | 2 | 190% | bar: WEEK 2 M to WEEK 3 W
2.2 | Switch to token authentication | Emilio, Emanuele | 5 | 7 | -2 | 2 | 2024-04-16 | 2024-04-20 | 5 | 140% | bar: WEEK 3 T to WEEK 3 W
2.3 | Spotify container and API calls | Emilio, Emanuele, Giuseppe | 10 | 6 | 4 | 2 | 2024-04-20 | 2024-04-24 | 2 | 60% | bar: WEEK 3 W to WEEK 3 T
2.4 | Spotify service integration | Emilio, Emanuele, Eric | 5 | 4 | 1 | 2 | 2024-04-20 | 2024-04-24 | 2 | 80% | bar: WEEK 3 W to WEEK 3 T
3 | Sprint 3 (October + extra summer days) |  | 40 | 47 | -7 |  |  |  | 18 | 117.5%
3.1 | ML readup and design (sprint 1) | Emanuele | 5 | 12 | -7 | 3 | 2024-08-22 | 2024-10-11 | 51 | 240%
3.2 | Song snippets system | Emilio | 5 | 5 | 0 | 3 | 2024-10-11 | 2024-10-11 | 1 | 100%
3.3 | Recommendations model rework (sprint 2) | Emanuele, Giuseppe, Eric, Emilio | 5 | 4 | 1 | 2 | 2024-10-26 | 2024-10-26 | 1 | 80% | bar: WEEK 5 M to WEEK 6 M
3.4 | Recommendations interface (sprint 2) | Emilio, Giuseppe | 10 | 7 | 3 | 2 | 2024-10-26 | 2024-10-26 | 2 | 70% | bar: WEEK 5 M to WEEK 6 M
3.5 | Interface improvements | Eric, Emilio, Giuseppe | 4 | 5 | -1 | 3 | 2024-10-11 | 2024-11-01 | 22 | 125% | bar: WEEK 5 M to WEEK 6 T
3.6 | Token payment (sprint 1) | Emilio, Giuseppe | 5 | 5 | 0 | 3 | 2024-10-11 | 2024-10-11 | 1 | 100%
3.7 | Token validations (sprint 1) | Emilio, Alessio | 6 | 5 | 1 | 2 | 2024-10-11 | 2024-10-11 | 1 | 83.33%
3.8 | Recommendation system with ML | Emanuele, Emilio, Giuseppe | 10 | 14 | -4 | 3 | 2024-10-11 | 2024-10-26 | 16 | 140% | bar: WEEK 5 M to WEEK 6 T
3.9 | Recommendation interface | Emilio, Giuseppe, Alessio | 10 | 10 | 0 | 3 | 2024-10-26 | 2024-10-30 | 5 | 100% | bar: WEEK 6 T to WEEK 6 T
3.10 | Review route and interface | Emilio, Emanuee, Giuseppe, Alessio | 5 | 8 | -3 | 3 | 2024-10-30 | 2024-11-02 | 2 | 100% | bar: WEEK 6 T to WEEK 6 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 222 | 294 | -65 | 66 | 3.3636 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
[10 empty] | PLAN | 222 | 222 | 222 | 222 | 218.6364 | 215.2727 | 211.9091 | 208.5455 | 205.1818 | 201.8182 | 198.4545 | 195.0909 | 191.7273 | 188.3636 | 185 | 181.6364 | 178.2727 | 174.9091 | 171.5455 | 168.1818 | 164.8182 | 161.4545 | 158.0909 | 154.7273 | 151.3636 | 148 | 144.6364 | 141.2727 | 137.9091 | 134.5455 | 131.1818 | 127.8182 | 124.4545 | 121.0909 | 117.7273 | 114.3636 | 111 | 107.6364 | 104.2727 | 100.9091
[10 empty] | ESTIMATE | 222 | 215 | 208 | 205 | 200 | 195 | 190 | 187 | 184 | 178 | 175 | 171 | 165 | 158 | 153 | 148 | 143 | 138 | 133 | 130 | 122 | 119 | 115 | 107 | 103 | 98 | 95 | 92 | 89 | 86 | 83 | 79 | 73 | 69 | 65 | 58 | 51 | 47 | 43 | 39
[10 empty] | HRS COMPLETED | 7 | 7 | 3 | 5 | 5 | 5 | 3 | 3 | 6 | 3 | 4 | 6 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 8 | 3 | 4 | 8 | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 4 | 6 | 4 | 4 | 7 | 7 | 4 | 4 | 4 | 3
[10 empty] | HRS REMAINING | 215 | 208 | 205 | 200 | 195 | 190 | 187 | 184 | 178 | 175 | 171 | 165 | 158 | 153 | 148 | 143 | 138 | 133 | 130 | 122 | 119 | 115 | 107 | 103 | 98 | 95 | 92 | 89 | 86 | 83 | 79 | 73 | 69 | 65 | 58 | 51 | 47 | 43 | 39 | 36